## Gate Status
THINKAI 2026 — AI-era Delivery Estimation Research
Gate 3B / Gate 4B status ¦ Route B synthetic mechanism evaluation
Workstream | Status | Evidence / Decision | Next control | Status summary
Gate 2 novelty pivot | Approved—conditional | Contribution narrowed to prospective role-stage capacity forecasting beyond Story Points and HIE-compatible baselines. | Finish executable searches and evidence map. | Complete / approved | 7
Gate 3 causal/construct model | Approved—Route B | Role–Stage Human Touch Demand, capacity pressure, queue delay, evidence readiness, verified delivery capacity. | Keep cognition and causal claims out of Route B. | Blocked / failed | 1
Gate 3B operational specification | Complete—not validated | Five formative drivers, four risk tiers, six gates, explicit Pass/Conditional/Fail semantics. | Future Route A expert/content validity. | Future | 1
Gate 4B minimum production DES | Complete—engineering pass | UTC calendars/blackouts, FIFO queues, DAG dependencies, evidence lifecycle, bounded rework and four role-stage functions implemented. | Retain production pre-lock hard stop.
Comparator + production runner | Complete—engineering pass | Five comparators; calendar-aware role-stage adapter; dual precision rules; calibration, sensitivity and immutable output contract. | Freeze only after release controls pass.
Development evaluation + ablations | Complete | 11 scenarios × 24 replications = 264 runs; four mechanism ablations; development outputs checksummed. | Synthetic development evidence only.
Independent Gate 4B audit | Complete—engineering pass | All 19 engineering-testable controls pass; unified verification passes 119/119 tests. | Production readiness remains a separate gate.
Locked synthetic evaluation | Blocked—not opened | Pre-lock returns hard_stop_not_ready; current checked-in manifest is prototype-only. | Close eight release-readiness controls; require ready_to_open.
Route A organizational validation | Future work | Required for human workload, construct validity, usability, causal and organizational claims. | Prospective multi-team shadow study.
Interpretation boundary | Synthetic mechanism evidence only; not empirical validation of human cognition, organizational delivery, or causal AI effects.
Last updated | 2026-08-14

## Development Results
Development-only Synthetic Results
Locked evaluation seeds were not opened.
Scenario | Family | Items (n) | Story Points Brier | HIE Brier | Simple Role Load Brier | Proposed Model Brier | Best deployable model | Interpretation
baseline_sp | development | 288 | 0.0012653 | 0.0030471 | 0.00025301 | 0.00031566 | Simple role load | Proposed model is not universally superior.
baseline_bottleneck | development | 288 | 0.0012653 | 0.0030471 | 0.00025301 | 0.00049064 | Simple role load | Role information helps; added readiness term does not here.
review_capacity_low | sensitivity | 576 | 0.031709 | 0.035752 | 0.03031 | 0.030685 | Simple role load | High review pressure narrows differences.
review_capacity_high | sensitivity | 576 | 0.0047801 | 0.011082 | 0.0013933 | 0.0026563 | Simple role load | Capacity relief improves completion calibration.
load_high | sensitivity | 864 | 0.37312 | 0.33372 | 0.40678 | 0.38373 | HIE-compatible | Proposed model underperforms SP and HIE in this stress case.
edge_severe_queue | adversarial development | 1152 | 0.46756 | 0.3772 | 0.52287 | 0.46033 | HIE-compatible | Adversarial case rejects universal advantage.
Parameter recovery
Scenario | Target multiplier | Recovered multiplier | Absolute error
recovery_service_low | 0.75 | 0.74135 | 0.0086492
recovery_service_high | 1.75 | 1.7299 | 0.02014
Run manifest checksum | e90b6b7107db0e36dc85e3c25d252372934749d52738c3e0fad4c781ba0092f7
Source files | simulation/output/development/ (4 CSVs + checksummed manifest)

## Audit Blockers
Independent Audit — Hard Stop Register
Verdict: ENGINEERING PASS; production evaluation remains blocked by release-readiness controls.
ID | Severity | Blocker | Evidence / Impact | Required remediation | Status
B1 | Critical | Mandatory gate failure can complete | Mandatory Fail cannot advance; terminal and bounded-rework semantics have regression coverage. | No further engineering action. | Closed
B2 | Critical | Gate contract ignored | Allowed states, evidence/readiness, risk applicability, conditional policy, freshness, invalidation and N/A rationale enforced. | No further engineering action. | Closed
B3 | Critical | Schema validator incomplete | Ranges, probabilities, durations, timestamps, references, ownership and transitions are validated. | No further engineering action. | Closed
B4 | Major | Minimum production mechanisms | Frozen narrow scope implements calendars/blackouts, FIFO queues, DAG dependencies, evidence lifecycle and four role-stage functions. | Maintain explicit exclusions and claim boundary. | Closed—narrowed scope
B5 | Critical | Comparator/config mismatch | Proposed comparator consumes role-stage demand/capacity, calendar availability, readiness, rework and dependency exposure. | No further engineering action. | Closed
B6 | Critical | Production release readiness | Eight pre-lock controls remain open; prototype seeds are ineligible for production. | Freeze protocol/release; independent review; externally sealed fresh seeds; runner/output readiness. | Open—hard stop
B7 | Major | Output contract incomplete | Dual precision, conditional sensitivity, reconciliation, checksums and fail-clean immutable publication are implemented. | No further engineering action. | Closed
B8 | Major | Default test discovery misleading | Unified test runner discovers both roots and passes 119/119 tests. | Use simulation.test_runner as the required command. | Closed

## Pending Work
Pending Work and Approval Gates
Priority | Item | Status | Completion gate | Human requirement
1 | Fix mandatory-gate transition defect | Complete | Regression tests prove Fail cannot advance. | No
2 | Strengthen schema and cross-reference validation | Complete | Invalid probabilities, durations, levels and references are rejected. | No
3 | Define/implement minimum production DES scope | Complete | All 19 engineering-testable Gate 4B controls pass. | No
4 | Unify verification and hard-stop wiring | Complete | Unified runner passes 119/119 tests; pre-lock fails closed. | No
5 | Complete Gate 2 executable searches | In progress | Complete authenticated searches, exports, deduplication, evidence matrix and PRISMA reconciliation. | Accountable author confirmation of citations
6 | Populate literature-informed parameter registry | In progress | Replace illustrative parameters or retain explicit sensitivity bounds with source locators. | Accountable author confirmation
7 | Independent Gate 4B agent audit | Complete | Engineering contract passed; production release readiness remains separate. | No; agent audit is software-only
8 | Freeze/register production package | Blocked—8 controls | Placeholder-free protocol, hashes, release, review, sealed seeds and readiness records. | Author approval required for external registration
9 | Run locked evaluation | Blocked—not authorized | Pre-lock must return ready_to_open before any production seed access. | No
10 | Route A prospective organizational validation | Future | Multi-team field data and genuine expert/content validation. | Yes—cannot be replaced by agents
Rule | Agents may support screening, extraction, software audit and synthetic stress testing; they cannot validate human cognitive load or organizational usefulness.

## Search Progress
Gate 2 Search Progress
Pilot/query engineering only—not PRISMA eligible.
Run | Family | Returned | Depth | Disposition
AX-P0 | Broad precision pilot | 643 | 5 | Precision failure; do not freeze
AX-S3 | Story Points / effort | 4 | 4 | Full-export candidate; sentinel test pending
AX-S4 | Review burden | 4 | 4 | Precise complementary family
AX-S6 | Lifecycle delivery | 2 | 2 | Sentinel recall failure; revise
AX-S5 | Assurance / verification | 142 | 5 | Split into review/testing/security
AX-S6R | Revised lifecycle delivery | 29 | 10 | Sentinel recall success; full-export candidate
Pending databases | Scopus; Web of Science; IEEE Xplore; ACM DL; SpringerLink; ScienceDirect
Next | Connect authenticated databases; then full pagination, exports, checksums, deduplication, agent screening/appraisal and PRISMA reconciliation.

## Parameter Registry
Literature-Informed Parameter Registry
Evidence anchors only—not a calibrated simulation parameter set.
ID | Mechanism | Class | Source | Permitted use | Prohibited inference
LP-001 | Favorable AI implementation speed | E1/L | Peng et al., arXiv 2302.06590 | Favorable sensitivity world | No universal 0.442 multiplier
LP-002 | Adverse mature-repository effect | E1/L | Becker et al., arXiv 2507.09089 | Adverse moderator world | No universal +19%
LP-003 | Story Point revision | E1 | Pasuksmit et al., 10.1007/s10664-022-10192-9 | Matching OSS-style baseline | Not an AI or gate-failure rate
LP-004 | SP + HIE + person heterogeneity | E1 | Alaswad et al., 10.1007/s10791-026-10331-6 | Comparator and heterogeneity design | No lifecycle distributions
LP-005 | Subjective workload dimensions | Instrument | NASA-TLX | Future Route A criterion | Not objective capacity/time
LP-006 | Measurement heterogeneity | L | Gonçales et al., 10.1016/j.infsof.2021.106563 | Wide measurement-error sensitivity | No workload-to-hours conversion
LP-007 | LLM Story Point prediction | E1 background | Shetty et al., arXiv 2603.06276v2 | Comparator family | Not SP construct validity
LP-008 | AI-labelled code review time | Candidate E1 | arXiv 2606.26505v1 | Prioritize full-text extraction | No numeric use until verified
Current gaps | Role service times, gate costs/failures, rework, UAT, switching and measurement overhead remain illustrative.